## Tabelle1
Phase | Time Estimate (days / 8h) | Cost | Comments | Hourly wage (EUR) | Working hours per day
Preparation Phase | 2 | 480 | Discussion with client, selecting the libraries for common components and creating boilerplate for the application based on ReactJS | 30 | 8
Sign Up / Sign In | 0.5 | 120
Password Change/Reset/Forgot | 1 | 240
Scrap the PDF data of the machines | 2 | 480 | Using the available PDFs of the machines catalogue write a backend endpoint that scraps the importand data and saves the input in the database
User Management | 1 | 240 | Detail page, edit, delete, last login,…
Machines Management | 2 | 480 | Show machines in different power classes. Select machine for calculation. Make card for motor similat to faulhaber calculator
Load points modal | 0.5 | 120 | Enter the load points data (speed, torque and temperature in SI units). Also add a settings modal for the graph generation (min, max torque, min. and max speed…)
Analytics and results presentation | 3 | 720 | Generate all graphs in python and send to frontend. This will replace the usage of chartjs and will enable simpler mainanance. The same is observed on the faulhaber calculator. The results are static and onClick events will not be possible
Machine details view | 3 | 720 | Pictures and other data of the machine have to be provided. The Bühler motor catalog is an example for the visual representation and data that is needed.
Fake database to MongoDB or other technology | 2 | 480 | Update backend to the new flask version. Swich from file system to real DB
Integration testing | 1 | 240
Deployment and Testing | 2 | 480 | Client should provide the server solution
Maintenance | ???
| Total Working Days | Total Cost (EUR)
| 20 | 4800