## Tabelle1
Phase | Time Estimate (days / 8h) | Cost | Comments | Hourly wage (EUR) | Working hours per day
Preparation Phase | 2 | 400 | Discussion with client, selecting the libraries for common components and creating boilerplate for the application based on ReactJS | 25 | 8
Sign Up | 1 | 200
Log In | 1 | 200
Password Change/Reset | 1 | 200
Forgot Password | 1 | 200
User Management | 2 | 400 | Detail page, edit, delete, last login,…
Machines Management | 2 | 400 | Show machines in different power classes. Select machine for calculation
Load points modal | 1 | 200
Analytics and results presentation | 5 | 1000
Machine details view | 3 | 600
Fake database to MongoDB or other technology | 2 | 400 | Update backend to the new flask version. Swich from file system to real DB
Integration testing | 1 | 200
Deployment and Testing | 2 | 400 | Client should provide the server solution
Maintenance | ???
| Total Working Days | Total Cost (EUR)
| 24 | 4800